## Sheet1
COSC1076 ¦ Semester 1 2021
Assignment 2 ¦ Weekly Update Tracking Sheet
Group Name: | YALG
Group Member: | Dominic Hu |  | Progress Classes: | Ahead
Group Member: | Philip Lee |  |  | On-track
Group Member: | Amiru Chandrasena |  |  | Behind
Group Member: | Runhui Zhou |  |  | Way Behind
Tutor: | Dale Stanbrough
Class: | Wednesday 8:30-10:30
|  | Week 7 | Goals | Tutor Notes | Indidvidual Updates | Dominic Hu | Philip Lee | Amiru Chandrasena | Runhui Zhou
|  |  | Group Formed |  | Weekly Contribution | Created Teams group and Git Repository | Cloned repository | Cloned Git Repository | Cloned Git Repository
|  |  | MS Team created |  | Issues
|  |  | Git Repo created |  | Other Notes
|  | Progress | On-track
|  | Week 8 | Goals | Tutor Notes | Indidvidual Updates | Dominic Hu | Philip Lee | Amiru Chandrasena | Runhui Zhou
|  |  | Choice of where to use linked list, vector & array |  | Weekly Contribution | Planned out assignment and divided into subtasks Allocated subtasks to each group member Finished skeleton implementation of GameBoard object | Began and finished working on Node class, Linked List class and Tile class. Save function implementation began. | Started creating skeleton implimentation of scrabble.cpp Implimented Main Menu and user prompt in cluding credits | started implementing Player and Hand Class. Also thinking about the load game function.
|  |  | Initial Design of ADTs (classes and potential methods) |  | Issues
|  |  | Main menu |  | Other Notes
User Prompt (for gameplay), but no/minimal error checking
Linked List implementation
Implementation(s) or suitable ADTs wrapper for the use of vector and arrays, game logic not required
ADT implementation for storing information, game loop logic not required
|  | Progress | On-track
|  | Week 9 | Goals | Tutor Notes | Indidvidual Updates | Dominic Hu | Philip Lee | Amiru Chandrasena | Runhui Zhou
|  |  | Load/Save to/from data strucutres (doesn't require integration with main menu or game loop) |  | Weekly Contribution | Added play game, new game, and input validation methods to scrabble.cpp Fixed issues with first GameBoard implementation Cleaned up input validation checking | Finished and refined save game function, including adding functions to Tile, Hand and GameBoard, and then objects error fixing for Tile, Node and Linked List classes | Created TileBag class and Initialisation linked list functionlaity and vectors. with reading in from file functionality implimented fixing and error checking on scrabble.cpp | Made some adjustment to Player and Hand class to meet what other components in this project need. Started to implement load game function according to save game function. Help modifies the LinkedList implementation.
|  |  | Initialisation of data strctures for new game |  | Issues
|  |  | Write Tests Cases for common uses |  | Other Notes
Gameplay for single round
|  | Progress | On-track
|  | Week 10 | Goals | Tutor Notes | Indidvidual Updates | Dominic Hu | Philip Lee | Amiru Chandrasena | Runhui Zhou
|  |  | Fully complete implementation and error free |  | Weekly Contribution | Fully implemented and working gameplay loop logic for tile placing, replacing, saving and quitting Fully implemented new game method using the finished classes Implemented game over condition checking and outcome Implemented BINGO functionality Fixed all instances of input validation in the application Added a tie game end condition Added a 2 consecutive passes when tile bag is empty end condition | Minor error fixing and refining of all functions and classes that were worked on. Tile, Node and Linked List classes are all fully functional, and the save function is completely implemented and error-free. 3 input test cases finished/ | Fully implemented and working Tilebag.cpp and TIlebag.h implimentation. Functions for getting tiles, removing tiles, ect.. implimented. Debugging and enhancement of code for better readability. Finished +5 test cases. Implimented and editied scrabbled.cpp input checking and clearing segmentation faults. Input test cases finished | Implemented Load Game function and fixed a lot of bugs about hand class and load game function. They should be fully functional. Did some load file format check.
|  |  | Full error checking of user prompt |  | Issues
Other Notes
Final Tests
Group Report Written
|  | Progress | Behind